## Project Tracker
VettdRE Sentiment Intelligence Terminal — Project Tracker
The Bloomberg Terminal of Real Estate ¦ 36-Week Implementation Plan ¦ ~35 New Files, 4 New DB Models, 10 New API Integrations
# | Phase | Module | Task | Key Files | Days | Dependencies | Status | Priority | Start | End | % Done | Acceptance Criteria | Notes
1 | Phase 1 | 1.1 Schema | Add sentiment enums to Prisma schema (7 enums) | prisma/schema.prisma | 1 | None | Not Started | P0 |  |  | 0% | Migration applies cleanly
2 | Phase 1 | 1.1 Schema | Add SentimentSignal model (24 fields + indexes) | prisma/schema.prisma | 1 | 1.1.1 | Not Started | P0 |  |  | 0% | Prisma generate succeeds | Core data table
3 | Phase 1 | 1.1 Schema | Add SentimentIndex model (18 fields + indexes) | prisma/schema.prisma | 0.5 | 1.1.1 | Not Started | P0 |  |  | 0% | Prisma generate succeeds | Computed indices
4 | Phase 1 | 1.1 Schema | Add SentimentAlert + SentimentWatchlist models | prisma/schema.prisma | 0.5 | 1.1.1 | Not Started | P0 |  |  | 0% | Prisma generate succeeds | User-facing models
5 | Phase 1 | 1.1 Schema | Run migration + generate client | CLI | 0.5 | 1.1.1-4 | Not Started | P0 |  |  | 0% | Migration on Supabase succeeds | Test on local first
6 | Phase 1 | 1.1 Schema | Create TypeScript types file | src/lib/sentiment/types.ts | 0.5 | 1.1.5 | Not Started | P0 |  |  | 0% | Types compile with zero errors | RawSignal, ClassifiedSignal, etc.
7 | Phase 1 | 1.2 Infra | Create adapter interface + base class | sentiment-source-adapter.ts | 2 | 1.1 | Not Started | P0 |  |  | 0% | Mock adapter runs successfully | Rate limit, retry, logging
8 | Phase 1 | 1.2 Infra | Create rate limiter (token bucket) | rate-limiter.ts | 1 | None | Not Started | P0 |  |  | 0% | Throttles burst requests correctly | Per-source limits
9 | Phase 1 | 1.2 Infra | Create ingestion scheduler | ingestion-scheduler.ts | 1.5 | 1.2.1 | Not Started | P0 |  |  | 0% | Scheduler invokes adapters on schedule | Staggered starts, graceful failure
10 | Phase 1 | 1.2 Infra | Create RawSignal type + validation | raw-signal.ts | 0.5 | 1.1.6 | Not Started | P1 |  |  | 0% | Validation catches malformed signals
11 | Phase 1 | 1.3 NLP | Create keyword pre-filter | keyword-filter.ts | 1.5 | None | Not Started | P0 |  |  | 0% | Filters 70-80% of irrelevant content | RE keywords, geo keywords, negative keywords
12 | Phase 1 | 1.3 NLP | Create classifier prompt template | classifier-prompt.ts | 1 | None | Not Started | P0 |  |  | 0% | Few-shot examples cover all 6 categories | System prompt + examples
13 | Phase 1 | 1.3 NLP | Create signal classifier (Claude batch) | signal-classifier.ts | 2 | 1.3.1, 1.3.2 | Not Started | P0 |  |  | 0% | Classifies 10 test signals with >0.7 accuracy | Haiku for classification, batch 10-20
14 | Phase 1 | 1.3 NLP | Wire classifier into ingestion pipeline | ingestion-scheduler.ts (mod) | 0.5 | 1.3.3, 1.2.3 | Not Started | P0 |  |  | 0% | End-to-end: adapter → filter → classify → store
15 | Phase 1 | 1.4 Geo | Create NYC boundary data (GeoJSON) | src/data/nyc-boundaries.json | 1 | None | Not Started | P0 |  |  | 0% | 5 boroughs, ~200 neighborhoods, ~180 zips | From NYC Dept of City Planning
16 | Phase 1 | 1.4 Geo | Create geo-boundaries module | geo-boundaries.ts | 1 | 1.4.1 | Not Started | P0 |  |  | 0% | Point-in-polygon lookup works for NYC | Lightweight, no GIS dependency
17 | Phase 1 | 1.4 Geo | Create GeoTagger (NER + geocoding + boundary) | geo-tagger.ts | 2 | 1.4.2 | Not Started | P0 |  |  | 0% | "Bushwick apartment" → correct geo chain | Uses existing Geocodio + PLUTO
18 | Phase 1 | 1.5 Trends | Create Google Trends adapter (SerpApi) | google-trends-adapter.ts | 2 | 1.2.1 | Not Started | P0 |  |  | 0% | Fetches trend data for 22 keywords × 6 markets | Demand + distress keyword sets
19 | Phase 1 | 1.5 Trends | Create trend baseline computation | trend-baseline.ts | 1 | 1.5.1 | Not Started | P0 |  |  | 0% | Z-scores produce sensible magnitudes | 12-month rolling baseline
20 | Phase 1 | 1.5 Trends | Add SERPAPI_KEY to env + settings page | settings/api-keys (mod) | 0.5 | None | Not Started | P1 |  |  | 0% | API key configurable in settings | Add to .env.example, cloudbuild.yaml
21 | Phase 1 | 1.5 Trends | Seed initial 6 markets + historical baseline | markets.ts config | 0.5 | 1.5.1, 1.5.2 | Not Started | P1 |  |  | 0% | NYC + 5 secondary markets seeded
22 | Phase 1 | 1.6 News | Create RSS parser module | rss-parser.ts | 1 | None | Not Started | P0 |  |  | 0% | Parses RSS/Atom feeds with dedup | Use rss-parser npm package
23 | Phase 1 | 1.6 News | Create news feed config (8 Tier 1 feeds) | news-feeds.ts | 0.5 | None | Not Started | P1 |  |  | 0% | All 8 Tier 1 RSS URLs configured | TRD, Bisnow, GlobeSt, etc.
24 | Phase 1 | 1.6 News | Create news adapter (RSS + Brave News) | news-adapter.ts | 2 | 1.6.1, 1.6.2, 1.2.1 | Not Started | P0 |  |  | 0% | Ingests + classifies articles from 8+ pubs | 30-min refresh Tier 1
25 | Phase 1 | 1.6 News | Extend Brave Search for news queries | brave-search.ts (mod) | 1 | None | Not Started | P1 |  |  | 0% | News queries return relevant results
26 | Phase 1 | 1.6 News | Wire news into classification pipeline | Pipeline integration | 0.5 | 1.6.3, 1.3.3 | Not Started | P0 |  |  | 0% | Articles classified + geo-tagged + stored
27 | Phase 1 | 1.7 Index | Create freshness decay function | freshness.ts | 0.5 | None | Not Started | P1 |  |  | 0% | Exponential decay: today=100, 7d=70, 30d=22 | Configurable λ per source
28 | Phase 1 | 1.7 Index | Create index computation engine | index-engine.ts | 3 | 1.1, 1.3, 1.4 | Not Started | P0 |  |  | 0% | MPI correct for NYC metro + 5 neighborhoods | Weighted category aggregation → MPI
29 | Phase 1 | 1.7 Index | Create trend computation module | trend-compute.ts | 1 | 1.7.2 | Not Started | P1 |  |  | 0% | 30/60/90-day MAs, YoY, percentile rank
30 | Phase 1 | 1.7 Index | Create computation scheduler + pruning | index-engine.ts (scheduler) | 0.5 | 1.7.2, 1.2.3 | Not Started | P1 |  |  | 0% | Metro: 2h, County: 4h, Neighborhood: 6h | Historical data pruning rules
31 | Phase 1 | 1.8 UI | Create /terminal route + page | terminal/page.tsx | 0.5 | None | Not Started | P0 |  |  | 0% | Route accessible, protected by auth | Server component
32 | Phase 1 | 1.8 UI | Create terminal dashboard layout | terminal-dashboard.tsx | 3 | 1.8.1 | Not Started | P0 |  |  | 0% | Header + grid + feed + AI panel placeholder | Client component, responsive
33 | Phase 1 | 1.8 UI | Create market card component | components/market-card.tsx | 2 | 1.7.2 | Not Started | P0 |  |  | 0% | MPI gauge + sparkline + trend arrow + top signal | Color-coded by MPI value
34 | Phase 1 | 1.8 UI | Create MPI gauge component | components/mpi-gauge.tsx | 1 | None | Not Started | P1 |  |  | 0% | Semicircular gauge, -100 to +100, animated | SVG-based
35 | Phase 1 | 1.8 UI | Create signal feed component | components/signal-feed.tsx | 1.5 | 1.7.2 | Not Started | P0 |  |  | 0% | Scrollable, filterable, auto-refresh 60s | Like message thread list pattern
36 | Phase 1 | 1.8 UI | Create server actions for terminal | terminal/actions.ts | 1 | 1.7.2 | Not Started | P0 |  |  | 0% | Watchlist, signals, summary endpoints work
37 | Phase 1 | 1.8 UI | Add Terminal to sidebar + mobile nav | sidebar.tsx, mobile-nav.tsx (mod) | 0.5 | 1.8.1 | Not Started | P1 |  |  | 0% | Terminal accessible from all nav surfaces | Activity or BarChart3 icon
38 | Phase 1 | 1.8 UI | Create watchlist management modal | terminal-dashboard.tsx | 1 | 1.8.6 | Not Started | P1 |  |  | 0% | Add/remove markets, drag reorder, plan gating
39 | Phase 1 | 1.9 Settings | Update API keys page for sentiment | settings/api-keys (mod) | 0.5 | 1.5.3 | Not Started | P1 |  |  | 0% | SerpApi status + test connection
40 | Phase 1 | 1.9 Settings | Create sentiment settings page | settings/sentiment/page.tsx | 1 | 1.8.1 | Not Started | P1 |  |  | 0% | Markets, alerts, frequency config saved
41 | Phase 1 | 1.9 Settings | Update feature gating for sentiment tiers | Feature gating logic | 0.5 | None | Not Started | P1 |  |  | 0% | Free: 3 markets. Explorer: unlimited. Pro: full.
42 | Phase 2 | 2.1 Reddit | Create Reddit adapter | reddit-adapter.ts | 2.5 | Phase 1 | Not Started | P0 |  |  | 0% | Posts + comments fetched, classified, stored | Reddit Data API + OAuth2
43 | Phase 2 | 2.1 Reddit | Create subreddit config | reddit-config.ts | 0.5 | None | Not Started | P1 |  |  | 0% | Market-to-subreddit mapping complete
44 | Phase 2 | 2.1 Reddit | Add REDDIT env vars + settings | ENV + settings (mod) | 0.5 | 2.1.1 | Not Started | P1 |  |  | 0% | API key configurable
45 | Phase 2 | 2.2 X/Twitter | Create X adapter (API v2) | x-adapter.ts | 2.5 | Phase 1 | Not Started | P0 |  |  | 0% | Posts fetched via search + filtered stream | Bearer token auth
46 | Phase 2 | 2.2 X/Twitter | Create X account tracking list | x-accounts.ts | 0.5 | None | Not Started | P1 |  |  | 0% | RE professionals, journalists curated per market
47 | Phase 2 | 2.2 X/Twitter | Add X_BEARER_TOKEN env var + settings | ENV + settings (mod) | 0.5 | 2.2.1 | Not Started | P1 |  |  | 0% | API key configurable
48 | Phase 2 | 2.3 Heat Map | Create sentiment map layer (Leaflet) | sentiment-layer.tsx | 3 | 1.7 | Not Started | P0 |  |  | 0% | Neighborhoods colored by MPI value on map | Polygon overlay with gradients
49 | Phase 2 | 2.3 Heat Map | Add to existing map layer controls | map-layers-renderer.tsx (mod) | 1 | 2.3.1 | Not Started | P0 |  |  | 0% | Toggle works alongside existing 14 layers
50 | Phase 2 | 2.3 Heat Map | Create time-lapse playback component | time-lapse.tsx | 2 | 2.3.1 | Not Started | P1 |  |  | 0% | 12-month scrubbing, play/pause, smooth transitions
51 | Phase 2 | 2.3 Heat Map | Create sentiment map server actions | sentiment-actions.ts | 1 | 1.7.2 | Not Started | P0 |  |  | 0% | getNeighborhoodMPI, getHistoricalMPI work
52 | Phase 2 | 2.4 AI Synth | Create AI synthesis engine | ai-synthesis.ts | 3 | 2.1, 2.2, 1.7 | Not Started | P0 |  |  | 0% | Daily briefing + market narrative + contrarian alerts | Uses existing Anthropic SDK pattern
53 | Phase 2 | 2.4 AI Synth | Create AI panel UI component | components/ai-panel.tsx | 2 | 2.4.1 | Not Started | P0 |  |  | 0% | Collapsible panel, markdown rendering, cited signals
54 | Phase 2 | 2.4 AI Synth | Create synthesis scheduler (daily 7AM) | ai-synthesis.ts (scheduler) | 0.5 | 2.4.1 | Not Started | P1 |  |  | 0% | Briefing generated + cached daily
55 | Phase 2 | 2.5 Building | Extend data-fusion-engine Phase 4 | data-fusion-engine.ts (mod) | 2 | 1.7 | Not Started | P0 |  |  | 0% | BuildingIntelligence includes sentiment property | Non-blocking Phase 4
56 | Phase 2 | 2.5 Building | Create sentiment section for building profile | sections/sentiment-section.tsx | 2 | 2.5.1 | Not Started | P0 |  |  | 0% | Neighborhood MPI + building signals displayed
57 | Phase 2 | 2.5 Building | Extend lead scoring with sentiment signals | lead-verification.ts (mod) | 1 | 2.5.1 | Not Started | P1 |  |  | 0% | Rising MPI +5, falling+distress +10
58 | Phase 2 | 2.6 Drilldown | Create market drilldown page | terminal/[market]/page.tsx | 3 | 1.7, 1.8 | Not Started | P0 |  |  | 0% | MPI chart + sub-indices + signal table + peers | Recharts for charting
59 | Phase 2 | 2.6 Drilldown | Create signal detail page | terminal/signal/[id]/page.tsx | 1.5 | 1.7 | Not Started | P1 |  |  | 0% | Full classification + context + related signals
60 | Phase 2 | 2.6 Drilldown | Create drilldown server actions | terminal/[market]/actions.ts | 1.5 | 1.7.2 | Not Started | P0 |  |  | 0% | Market detail + signal detail + comparable markets
61 | Phase 3 | 3.1 TikTok | Create TikTok adapter | tiktok-adapter.ts | 3 | Phase 2 | Not Started | P0 |  |  | 0% | Geo-tagged content volume + engagement tracked | Research API + Apify fallback
62 | Phase 3 | 3.2 YouTube | Create YouTube adapter | youtube-adapter.ts | 2.5 | Phase 2 | Not Started | P1 |  |  | 0% | 200+ channels monitored, transcripts analyzed | YouTube Data API v3 (free)
63 | Phase 3 | 3.3 Yelp | Create Yelp business activity adapter | yelp-adapter.ts | 2 | Phase 2 | Not Started | P1 |  |  | 0% | Business openings/closures per neighborhood | Yelp Fusion API (free 5K/day)
64 | Phase 3 | 3.4 Jobs | Create jobs & employment adapter | jobs-adapter.ts | 3 | Phase 2 | Not Started | P0 |  |  | 0% | Job volume by metro, corporate relocations tracked | Bright Data or direct API
65 | Phase 3 | 3.5 Migration | Create U-Haul migration index | uhaul-adapter.ts | 1.5 | Phase 2 | Not Started | P1 |  |  | 0% | One-way pricing ratios for 50 metro pairs | Weekly scrape
66 | Phase 3 | 3.6 Listings | Create listing language NLP adapter | listings-nlp-adapter.ts | 3 | Phase 2 | Not Started | P0 |  |  | 0% | Concession %, urgency %, amenity inflation tracked | StreetEasy + Brave Search
67 | Phase 3 | 3.7 Time-lapse | Enhance time-lapse with annotations + export | time-lapse.tsx (mod) | 2 | 2.3.3 | Not Started | P2 |  |  | 0% | Event annotations + GIF export
68 | Phase 4 | 4.1 Insurance | Create insurance market adapter | insurance-adapter.ts | 3 | Phase 3 | Not Started | P1 |  |  | 0% | Insurer withdrawals, premium changes tracked | Public data scraping
69 | Phase 4 | 4.2 Mobility | Create foot traffic integration | mobility-adapter.ts | 3 | Phase 3 | Not Started | P1 |  |  | 0% | Foot traffic by neighborhood from SafeGraph | Enterprise API
70 | Phase 4 | 4.3 Construction | Create construction cost index | construction-adapter.ts | 2 | Phase 3 | Not Started | P2 |  |  | 0% | BLS PPI + ENR index tracked | Free BLS API
71 | Phase 4 | 4.4 STR | Create STR regulatory tracker | str-adapter.ts | 2 | Phase 3 | Not Started | P2 |  |  | 0% | Council agendas scanned for STR items
72 | Phase 4 | 4.5 Permits | Create permit velocity time-series (z-scores) | permit-velocity.ts | 2 | Phase 3 | Not Started | P1 |  |  | 0% | 90-day rolling avg vs. 12-month baseline | Extends existing DOB data
73 | Phase 4 | 4.6 Alerts | Build advanced alert system + email digests | alert-engine.ts + email templates | 4 | Phase 3 | Not Started | P0 |  |  | 0% | Threshold + velocity + divergence alerts via email
74 | Phase 5 | 5.1 Framework | Refactor adapters to market-agnostic framework | All adapters (refactor) | 5 | Phase 4 | Not Started | P0 |  |  | 0% | Adapters accept market config, not hardcoded NYC | Strangler fig pattern
75 | Phase 5 | 5.2 Markets | Onboard Miami + Austin + Nashville + LA + Chicago | Market configs | 15 | 5.1 | Not Started | P0 |  |  | 0% | All 6 markets fully operational | ~3 days per market
76 | Phase 5 | 5.3 Cross-mkt | Create cross-market comparison views | terminal/compare/page.tsx | 5 | 5.2 | Not Started | P1 |  |  | 0% | National rankings, peer analysis, migration flows
77 | Phase 5 | 5.4 API | Create REST API for indices (Enterprise) | api/sentiment/route.ts | 4 | 5.2 | Not Started | P1 |  |  | 0% | API access with rate limiting by plan tier
TOTAL |  |  |  |  | 137

## Phase Summary
Phase Summary — Sentiment Intelligence Terminal
Phase | Weeks | Tasks | Est. Days | Goal | Key Deliverables | New APIs Required | Ship Gate
Phase 1: Foundation | 1-6 | 41 | ~42 | Core pipeline + Google Trends + News + Terminal UI | Ingestion pipeline, NLP classifier, GeoTagger, Google Trends adapter, News adapter, Index engine, /terminal dashboard, Watchlist | SerpApi ($50/mo) | MPI displayed for NYC metro + 5 boroughs with real data from Trends + News
Phase 2: Social Layer | 7-12 | 21 | ~30 | Reddit + X + Heat map + AI synthesis + Building integration | Reddit adapter, X adapter, Sentiment heat map layer, AI synthesis panel, Building profile sentiment section, Signal drilldowns | X API Basic ($100/mo), Reddit API (free) | Social signals flowing, heat map on Market Intel map, daily AI briefings generated
Phase 3: Alt Data | 13-20 | 7 | ~17 | TikTok, YouTube, Yelp, Jobs, Migration, Listing NLP | 6 new adapters, enhanced time-lapse, 100+ signals/day for NYC | TikTok API, YouTube API (free), Yelp API (free), Apify ($49/mo), Bright Data | All 6 adapters operational, signal volume significantly increased
Phase 4: Enterprise | 21-28 | 6 | ~16 | Insurance, mobility, construction, STR, permits, advanced alerts | 4 new adapters, permit velocity z-scores, email digest alerts | SafeGraph ($$$) | Enterprise signals operational, email alerts delivered
Phase 5: Multi-Market | 29-36 | 4 | ~29 | Expand to Miami, Austin, Nashville, LA, Chicago + API access | Market-agnostic framework, 5 new markets, cross-market views, REST API | None (reuses existing) | 6 markets operational, API access for enterprise tier

## API Costs
API Cost Breakdown — Sentiment Intelligence Terminal
Service | Env Variable(s) | Purpose | Monthly Cost | Phase | Notes
SerpApi | SERPAPI_KEY | Google Trends programmatic access | 50 | Phase 1 | Can start with $50/mo plan (5K searches)
Brave Search | BRAVE_SEARCH_API_KEY | News search, entity research | 0 | Phase 1 | Already integrated — existing cost
Anthropic Claude | ANTHROPIC_API_KEY | NLP classification + synthesis | 50 | Phase 1 | Estimate: ~$50/mo for classification volume. Already integrated.
Reddit API | REDDIT_CLIENT_ID/SECRET | Subreddit posts & comments | 0 | Phase 2 | Free for research/commercial use
X API v2 (Basic) | X_BEARER_TOKEN | Tweet search & filtered streams | 100 | Phase 2 | Basic tier. Upgrade to Pro ($5K) if volume requires
TikTok Research API | TIKTOK_API_KEY | Content metadata & geo-tags | 0 | Phase 3 | Free for research. Commercial may require partnership.
Apify (fallback) | APIFY_API_TOKEN | TikTok/Instagram scraping | 49 | Phase 3 | Starter plan. Scale as needed.
YouTube Data API v3 | YOUTUBE_API_KEY | Video metadata & transcripts | 0 | Phase 3 | Free (10K units/day quota)
Yelp Fusion API | YELP_API_KEY | Business openings/closures | 0 | Phase 3 | Free (5K calls/day)
Bright Data | BRIGHTDATA_API_KEY | Indeed/LinkedIn job scraping | 200 | Phase 3 | Estimate. Depends on volume.
SafeGraph/Placer.ai | SAFEGRAPH_API_KEY | Foot traffic data | 500 | Phase 4 | Enterprise pricing. Can defer.
Geocodio | GEOCODIO_API_KEY | Address geocoding | 0 | Phase 1 | Already integrated — free tier (2.5K/day)
FRED API | FRED_API_KEY | Mortgage rates, economic data | 0 | Phase 1 | Already integrated — free
TOTAL MONTHLY (all phases) |  |  | 949
Phase 1 Monthly Cost |  |  | 100 |  | SerpApi $50 + Claude ~$50 (existing infra)

## Dependencies
Critical Path & Dependencies
Module | Depends On | Blocks | Notes
1.1 Schema | Nothing (start here) | Everything in Phase 1 | CRITICAL PATH: Must complete first
1.2 Infra | 1.1 Schema | 1.3 NLP, 1.5 Trends, 1.6 News | Adapter interface used by all data sources
1.3 NLP | 1.1 Schema, 1.2 Infra | 1.4 Geo, 1.6 News pipeline, 1.7 Index | Claude classifier is core of pipeline
1.4 Geo | 1.1 Schema, 1.3 NLP | 1.7 Index (needs geo-tagged signals) | Can parallelize boundary data + GeoTagger
1.5 Trends | 1.2 Infra | 1.7 Index (needs signal data), 1.8 UI | Can start once adapter interface exists
1.6 News | 1.2 Infra, 1.3 NLP | 1.7 Index, 1.8 UI | RSS parser can start in parallel
1.7 Index | 1.1, 1.3, 1.4, 1.5/1.6 (signal data) | 1.8 UI, Phase 2 (all) | CRITICAL PATH: No UI without indices
1.8 UI | 1.7 Index engine | Phase 1 ship gate | Can scaffold layout while waiting for data
1.9 Settings | 1.5 (API keys), 1.8 (routes) | Phase 1 ship gate | Low priority, can defer
Phase 2 | Phase 1 complete | Phase 3 | Social adapters + heat map + AI synthesis
Phase 3 | Phase 2 complete | Phase 4 | 6 new data source adapters
Phase 4 | Phase 3 complete | Phase 5 | Enterprise signals + alerts
Phase 5 | Phase 4 complete | Launch | Multi-market expansion
CRITICAL PATH: 1.1 Schema → 1.2 Infra → 1.3 NLP → 1.4 Geo → 1.7 Index → 1.8 UI → Ship